## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Set the envirorment | 1 | 19/03/2024 | - I configured the project environment and removing the boilerplate this allowed me to work on core styles while making adjustments throughout development. -After setting up the environment, I created the initial repository and prepared it for version control. Each branch represents a user story, making it easier to track progress.
User Story #1 Creation of header and navigation | 4 | 19/03/2024 | -Creating the header and defining the app layout for both desktop and mobile devices, based on the style guide, was challenging. This led me to explore and learn Vue.js in more depth.
User Story #2 Overview of houses | 6 | 20/03/2024 | -Working with information from the API and continuously learning its capabilities was an exciting and engaging part of the project because I keep learning around this.
User story #3 Search bar and functionality User story #4 Sort by price and size | 6 | 21/03/2024 | -I implemented a search bar with functions to find and retrieve information.
User stoy #5 Details of the house | 6 | 22/03/2024 | - Integrating the listing view with the detailed view proved to be a challenge, but it helped me understand how to effectively use Pinia for state management.
User story #6 Create listing User Story #7 Edit (without delete) User Story #8 Owner can edit | 6 | 25/03/2024 | -This task was one of the most challenging because I had to learn how to implement what the API requested , I create a component that has almost the same information (Edit/Create) but with condictionals that help to display the right information.
User story #9 Delete listing | 4 | 29/03/2024 | -Creation of the component Delete listing and work in the conection with the single listing and the store that has nested multiple functions to make it work
Final details | 4 | 29/03/2024 | -Organizing the last details, styles and refactoring some code, it was great to learn how pinia works and the experience of working with vue even when I had no previous experience with the framework, it was really fun!
Total amount of hours | 37